## Daily Progress Report
NFT DIGITAL MARKETPLACE - DAILY PROGRESS TRACKING REPORT
Project: NFT Digital Marketplace Dashboard ¦ Tech: HTML5, CSS3, JS (ES6+), Bootstrap 5, Chart.js, LocalStorage
Date | Day | Task / Module | Planned Work | Completed Work | Pending Work | Issues / Bugs | Status | Progress % | Remarks
2026-10-14 | Day 1 | UI Architecture & Design System | Analyze Figma screens, define CSS variables (#121025 background, #1e1b38 cards, #735bf2 accents), set up typography & shared assets | Complete design tokens, folder structure, 12 vector NFT artworks, creator avatars, responsive grid & CSS components | None | None | Completed | 100% | Dark theme foundation established with smooth light theme compatibility
2026-10-14 | Day 1 | Shared Navigation & Header | Build sticky desktop sidebar, mobile off-canvas drawer, top search bar with live dropdown, theme toggle & profile menu | Sidebar with active links, responsive header, notification bell with badge & dropdown, instant NFT search, theme switcher | None | None | Completed | 100% | Unified navigation across all pages; smooth collapse on mobile viewports
2026-10-14 | Day 1 | Home Dashboard (index.html) | Implement hero banner, trending bids filter (All/Artwork/Book), Chart.js ETH price & Doughnut stats, top creators, active bids table | Full hero with live featured countdown, category filter pills, interactive Chart.js charts, follow/unfollow creators, active bids | None | None | Completed | 100% | Charts styled with purple gradient; live countdown updates every second
2026-10-14 | Day 1 | Bids Dashboard (bids.html) | Create bids summary KPI cards (Artworks, Auctions, Creators, Cancelled), active bids data table with checkboxes and actions | 4 KPI stat cards, full interactive bids table with countdowns, row selection, row cancel action, and Place Bid trigger | None | None | Completed | 100% | Connects directly to universal bid modal with amount validation
2026-10-14 | Day 1 | Saved Items (saved.html) | Build wishlist grid, filter by category/sorting, remove from saved, empty state with illustration & explore CTA | Saved items grid loaded from LocalStorage, toggle save heart icon, instant removal with toast, responsive empty state | None | None | Completed | 100% | State synchronizes seamlessly with Home and Collections
2026-10-14 | Day 1 | Collections (collections.html) | Build collections page with category filter (All, Artwork, Book, 3D Art, Metaverse), search input, sorting dropdown & details modal | Responsive NFT card grid, instant search filter, price/recency sorting, category pill buttons, bid modal launch | None | None | Completed | 100% | Consistent card heights, image ratios, and badge styling
2026-10-15 | Day 2 | Profile Management (profile.html) | User header with banner, verification badges, stats counters, tabs for My Bought, My Collections, Following list, Edit Profile modal | Complete profile layout, verified creator badge, 2FA status, dynamic bought/collected tabs, follow/unfollow toggle, edit profile persistence | None | None | Completed | 100% | LocalStorage stores edited full name, username, bio, and avatar instantly
2026-10-15 | Day 2 | Settings Multi-Tab (settings.html) | Create 6 settings tabs: Profile, Application, Security, Activity, Payment Method, API key management without full page reloads | All 6 tabs functional: theme/notification preferences, password form with strength check, session table, demo card/wallet, API key mask/copy | None | None | Completed | 100% | Clear simulated demo badges for wallets and API security
2026-10-15 | Day 2 | Authentication (login & register.html) | Create sleek login and register pages with form validation, show/hide password, demo credentials button, session persistence | Complete dark theme auth screens, email/password validation, session state stored in LocalStorage, logout flow to login.html | None | None | Completed | 100% | Quick-fill demo account button provided for immediate testing
2026-10-15 | Day 2 | NFT Details Page & Universal Modal | Standalone nft-details.html and reusable modal with high-res art, attributes, creator info, countdown, bid history, bidding form | Full NFT details page with dynamic query param loading, tabbed history & attributes, plus modal triggerable from every card | None | None | Completed | 100% | Validates bid amounts, verifies minimum bid rule, logs transaction history
2026-10-15 | Day 2 | Data Store & LocalStorage Architecture | Centralized data engine in js/data.js managing NFTs, bids, saved items, profile data, activity logs, and theme preferences | Reactive data store with automated fallback seeding, bid placement logic, wishlist toggling, and multi-tab sync | None | None | Completed | 100% | Zero code duplication across pages
2026-10-16 | Day 3 | Responsive Optimization (320px - 1920px) | Test and polish across 16 specified viewports: 320, 360, 375, 390, 414, 480, 576, 768, 820, 1024, 1152, 1280, 1366, 1440, 1600, 1920px | Off-canvas mobile menu, horizontal scrolling tables with touch support, auto-fitting CSS grid, flexible hero typography, zero layout overflow | None | None | Completed | 100% | Passed all breakpoint checks cleanly
2026-10-16 | Day 3 | Quality Assurance & Interactive Polish | Validate all forms, keyboard focus outlines, toast feedback, countdown timers, search highlights, dark/light theme persistence | All interactive triggers tested, console error free, toast notifications for all user actions, comprehensive README documentation | None | None | Completed | 100% | Final checklist 100% verified against project specifications